## Sheet1
CRTP: Updated Timeline (Chronological Overall)
Activities | Timeline | Responsibility | Status | Note
Purchase Docufide licensing agreement for all CCCS colleges | Aug. 2012 | CCCS IT | In progress
Hire a Degree Audit Coordinator | Aug. 2012 | CCCS Provost | Completed
Hire Research Associate/Program Coordinator | Nov. 2012 | CDHE/Project Director | Completed
CDHE coordinates RT working group to network and share lessons learned with one another | Year 1: Oct. 2012 Year 2: Sept 2013 Year 3: Sept 2014 | CDHE/Project Director | Year 1 completed; Year 2 in progress
Policy Audit for Office of Community College Research and Leadership (OCCRL) | Dec. 2012 | CDHE/Project Manager | Completed
Policy Implementation Study (OCCRL) | Ongoing, beginning Dec. 2012 | CDHE/Director of Research Project Manager | In progress
Coordinate the 13 CCCS registrar offices to ensure the audits are run for the appropriate institutions and the correct institutions are granting the degrees | Ongoing, beginning Dec 2012 | CCCS/Degree Audit Coordinator | In progress
Automate the 4-year and 2-year institutions' course equivalencies by entering all 4-year institutions' catalogs in the CCCS degree audit system (Banner System) | Dec. 2012: partner pilot institutions Oct. 2013: Year 1 grant partners June 2014: all 4-year colleges | CCCS/Degree Audit Coordinator | In progress
8-hour training retreats are hosted each semester | Feb 2013 and each term after | CCCS Provost and Degree Audit Coordinator | In progress | 2/15/13 Transfer Conference
Fall 2012 Course File Data Received | Feb. 2013 | CDHE/Research Director Project Manager | Completed
Coordinate with OCCRL on Baseline Report | Feb. 2013 | CDHE/Director of Research Project Manager | Completed
Host the annual Colorado Transfer Academy | Spring/Summer 2013 Spring/Summer 2014 Spring/Summer 2015 | CDHE/Project Manager, CCCS/Degree Audit Coordinator | Year 1 completed | Colorado Adult Learning Symposium
Cohort Analysis (OCCRL) | Spring 2013 Fall 2013 Spring 2014 | CDHE/Director of Research Project Manager | Year 1 completed
Design a statewide transfer/marketing campaign focusing on 4-year stop outs and traditional-age students | May 2013, ongoing | CDHE/ Communications Officer, Project Manager, Project Director | In progress
Identify any news articles in CO regarding RT for website and OCCRL | Ongoing beginning June 2013 | CDHE/Communications Officer, Project Manager | In progress | Continuing project
Revisit student survey that was created to pilot the first reverse transfer program in Colorado; gather lessons learned | Aug. 2013 | CDHE/Project Manager | Completed | received survey report from MSUD
Integrate language about RT into CDHE transfer policy | Aug. 2013 | CDHE/Project Manager/GE Council | In progress
Draft copy for letters to students | Sept. 2013 | CDHE | Pending approval from committee
Develop website | Aug.-Oct. 2013 | CDHE/Communications Officer, Project Manager | In progress
Program Report Due (Lumina) | Sept. 2013 | CDHE/Project Director Project Manager | Completed
Financial Report Due (Lumina) | Sept. 2013 | CDHE/Project Director Project Manager | Completed
Website goes live | Oct. 2013 | CDHE
RT newsletters to advisors at community colleges and 4-years (each semester through next two years) | Ongoing beginning Oct. 2013 | CDHE/Communications Officer | In progress
Develop video explaining RT for website | Aug.-Nov. 2013 | CDHE/Communications Officer and Project Manager working with Contractor | Working with contractor
Create webinar for introduction/refresher on RT (targeted to registrars) | Semesterly beginning Oct. 2013 | CDHE/Communications Officer and Project Manager | In progress
Analyze and evaluate the patterns of Colorado transfer students | Oct.-Nov. 2013 July 2014 | CDHE/IR Staff | In progress
Identify and track RT eligible students | Nov 2013: course data July 2014 | CDHE/Institutional Research Staff | In progrees | Jim's data pull
Letters to students regarding eligibility for RT (from four-year/DHE) | Nov.-Dec. 2013 | CDHE/Communications Officer works with four-years | In progress
Develop appropriate avenue to sustain RT; possible integration into GE Council | Nov. 2013 | CDHE/Lt. Gov. Project Director
Continue to identify CDHE and CCCS policies that can be strengthened to support reverse transfer | Nov. 2013 Ongoing | CDHE/Project Director GE Council
Contact with IHEs regarding first awarding of degrees | Dec. 2013- Jan. 2014 | CDHE
Letters to students regarding awarding of RT (from community college) | Dec. 2013 (depends on Parchment) | CCCS
First Degrees Awarded | Dec. 2013-Jan. 2014 | CCCS
Automate download of electronic transcripts into CCCS Banner System | Jan. 2014: Year 1 and 2 grant partners May 2014: all public 4-year institutions | CCCS IT and Consultants Docufide and Ellucian | In progress
Press release regarding reverse transfer | Jan. 2014 | CDHE/Lt Governor
Targeted outreach to stop outs begins | Jan. 2014 | CDHE/Communications Officer and Project Manager
Emails sent to stop outs | Jan. 2014 | CDHE/IHEs
Counselors/advisors will reach out to students who do not meet A.A./A.S./A.G.S. degree requirements to share information about what they must to do complete degree e.g., courses needed, etc. | Ongoing, each end of term beginning Jan. 2014 | CCCS Degree Audit Coordinator; CCCS Registrar Offices
First draft of implementation guide completed (targeted to registrars/IT depts) | Feb. 2014 | CDHE/Communications Officer and Project Manager
Postcards sent to stop outs | Feb. 2014 (as needed) | CDHE/IHEs
Calls to stop outs | Feb. - Mar. 2014 (as needed) | CDHE/IHEs
Host event for stop outs/attend job fairs | Mar. 2014 (as needed) | CDHE
Emails to RT-eligible students (at 4-years) | April 2014 | CDHE/IHEs
Letters to students regarding awarding of RT (from community college) | May 2014 | CCCS
Contact with IHEs regarding awarding of degrees to students and stop outs | May 2014 | CDHE
Award initial stop out degrees | May 2014 | CCCS
Award non-stop out RT degrees | May 2014 | CCCS
Prepare annual report for stakeholders including policy makers and press | July 2014 | CDHE/Project Director
Document each step required to successfully create and implement a statewide reverse transfer program | July 2014 | CDHE/Project Director Project Manager CCCS/Provost
Second round of emails, postcards, etc to stop outs | Aug. - Oct 2014 | CDHE/IHEs
Emails to RT-eligible students (at 4-years) | Sept. 2014 | CDHE/IHEs
Letters to students regarding awarding of RT (from community college) | Oct. 2014 | CCCS
Contact with IHEs regarding awarding of degrees to students and stop outs | Oct. 2014 | CDHE
Award last set of stop out degrees | Oct. 2014 | CCCS
Award non-stop out RT degrees | Oct. 2014 | CCCS
Distribute implementation guide to all institutions | Nov. 2014 | CDHE
Update website | Nov. 2014 | CDHE
Program Report Due (Lumina) | Nov. 2014 | CDHE/Project Director Project Manager
Financial Report Due (Lumina) | Nov. 2014 | CDHE/Project Director Project Manager
Set calendar for communications efforts and awarding degrees moving forward, to include: | Dec. 2014 | CDHE
*RT degree awards cycle (February, May, October awards)
*letters to RT-eligible students (from 4-year)
*letters to IHEs (from DHE)
*letters to RT-awarded students (from comm college)
Conclude Lumina Grant and deliver following: | Dec. 2014 | CDHE/Project Director Project Manager
• Provide an implementation guide for other states and institutions interested in developing reverse transfer programs
• Develop and provide an online resource for students to be able to access information about reverse transfer
• Inform staff involved in reverse transfer program about how to support students to obtain the degrees to which they are entitled